## MLOps Implementation Estimates
Phase Activity | Complexity | Team Size | Average Effort Hours (Planning & Designing) | Average Effort Hours (Code Development) | Average Effort Hours (Unit Testing & Promotion) | Average Effort Hours (Documentation) | Average Effort Hours | Work Effort in Days | Task Date of Completion
Business Requirements
Functional Specifications
Detailed Design
Code and Unit Test
System Testing
User Acceptance Testing
Environment Setup and Access (includes persona, service, Repo access, Jira etc as well) | 2 | [5 empty] | 36 | 4.5
Use-case identification and design approval. Code walkthrough | 2 | [5 empty] | 36 | 4.5
Gitlab Repo and CI/CD approach | 2 | [5 empty] | 80 | 10
Data read and Ingestion | 2 |  | 4 | 16 | 4 | 2 | 26 | 3.25
Data Labeling | 2 | [5 empty] | 0
Data processing (pre/post/wrangling) | 2 |  | 4 | 25 | 4 | 2 | 35 | 4.375
Data split (train/test/val) | 3 |  | 1 | 6 | 2 | 1 | 10 | 1.25
Data storage (format conversion) | 3 |  | 6 | 16 | 2 | 1 | 25 | 3.125
Feature Store Creation | 1 | [5 empty] | 0 | 0
Data Validation (schema, rule) | 2 | [5 empty] | 0 | 0
Data statistics generation (EDA) | 2 |  | 6 | 24 | 8 | 2 | 40 | 5
EDA (vizualization) - Tensorboard etc | 2 |  | 4 | 16 | 8 | 2 | 30 | 3.75
metadata generation & lineage | 2 |  | 1 | 8 | 2 | 1 | 12 | 1.5
Hyperparameter tuning | 2 |  | 6 | 24 | 6 | 2 | 38 | 4.75
Model Training | 1 |  | 6 | 32 | 6 | 2 | 46 | 5.75
Model Training pipeline (with specifics such as machine type, configs etc) | 1 |  | 2 | 18 | 6 | 2 | 28 | 3.5
Model Evaluation | 1 |  | 6 | 28 | 6 | 2 | 42 | 5.25
Model metadata tracking and validation | 2 |  | 3 | 28 | 6 | 2 | 39 | 4.875
Unit testing | 2 | [5 empty] | 0 | 0
Model registry create | 1 |  | 6 | 28 | 6 | 2 | 42 | 5.25
Model Deployment (batch) | 1 |  | 6 | 30 | 6 | 2 | 44 | 5.5
Model serving Endpoint Creation | 1 |  | 6 | 24 | 6 | 2 | 38 | 4.75
Model Deployment on endpoint | 1 |  | 6 | 24 | 6 | 2 | 38 | 4.75
Batch Prediction Job create (online/offline) | 1 |  | 6 | 28 | 6 | 2 | 42 | 5.25
Enable Model Monitoring and Alerting (vertex) | 2 |  | 4 | 32 | 6 | 2 | 44 | 5.5
data drift and alerting (vertex) | 2 |  | 4 | 18 | 6 | 2 | 30 | 3.75
Model Monitoring and Alerting (custom) | 1 |  | 6 | 32 | 6 | 4 | 48 | 6
data drift and alerting (custom) | 1 |  | 6 | 36 | 6 | 4 | 52 | 6.5
Model Explainability | 3 |  | 4 | 18 | 6 | 2 | 30 | 3.75
Model Serving pipelines | 1 |  | 4 | 42 | 8 | 4 | 58 | 7.25
Result mapping (after prediction if any) | 2 |  | 4 | 32 | 8 | 4 | 48 | 6
Cloud monitoring for custom monitoring | 1 |  | 4 | 30 | 8 | 4 | 46 | 5.75
Setting up logging and lineage | 2 |  | 4 | 18 | 6 | 2 | 30 | 3.75
Unit test case intergration in ci/cd | 2 |  | 4 | 18 | 6 | 2 | 30 | 3.75
other tests intergation with Ci/CD | 3 |  | 4 | 18 | 6 | 2 | 30 | 3.75
Develop Ci/CD for Terraform infra provisioning | 2 |  | 4 | 18 | 6 | 2 | 30 | 3.75
Integrate Terraform provisioning with CI/CD | 1 |  | 4 | 18 | 6 | 2 | 30 | 3.75
Create CI/CD cofig files and setup | 2 |  | 4 | 18 | 6 | 2 | 30 | 3.75
Terraform scripts | 1 |  | 6 | 32 | 8 | 2 | 48 | 6
cloud function create for custom jobs | 1 |  | 4 | 40 | 8 | 2 | 54 | 6.75
cloud shceduler create for triggering events | 1 |  | 4 | 20 | 6 | 2 | 32 | 4
Airflow code to orchestrate ML pipelines | 1 |  | 12 | 50 | 12 | 6 | 80 | 10
Airflow code to orchestrate inferencing pipeline | 1 |  | 12 | 50 | 12 | 6 | 80 | 10
Airflow config setup | 1 |  | 6 | 12 | 6 | 2 | 26 | 3.25

## Sheet1
MLOps Implementation Estimates
Client Name - General Mills Inc.
Project Name- Walmart Engine