## GMI MLOPS - Phase1
Data Science Lifecycle | Description | Estimations
Set up of experimentation and tracking process with visualization | Data read and Ingestion | 3.25
| Data processing (pre/post/wrangling) | 4.375
| Data split (train/test/val) | 1.25
| Data storage (format conversion) | 3.125
| Data statistics generation (EDA) | 5
| EDA (vizualization) - Tensorboard etc | 3.75
| Metadata generation & lineage | 1.5
| Hyperparameter tuning | 4.75
| Model Training | 5.75
| Model Training pipeline (with specifics such as machine type, configs etc) | 3.5
| Model Evaluation | 5.25
| Model metadata tracking and validation | 4.875
Build a centralized model registry | Model registry create | 5.25
| Model Deployment (batch) | 5.5
| Model serving Endpoint Creation | 4.75
| Model Deployment on endpoint | 4.75
Model Industrialization Approach
Set up alert mechanism for model and data drift detection | Enable Model Monitoring and Alerting (vertex) | 5.5
| Data drift and alerting (vertex) | 3.75
| Model Monitoring and Alerting (custom) | 6
| Data drift and alerting (custom) | 6.5
Monitoring (model & data)
• Set up vertex-based model & data monitoring | Cloud monitoring for custom monitoring | 5.75
Set up standard cloud logging and monitoring for services (with visualization) | Setting up logging and lineage | 3.75
| Model Explainability | 3.75
Software Engineering
Establish branching strategy and code promotion with proper release management | Gitlab Repo and CI/CD approach | 10
Architecture
Create modularized / microservices-based framework for seamless customizations at later stages | Define the Microservices
Choose a Deployment Platform
Develop the Microservices
Integrate the Microservices
Containerize the Microservices:
Manage and Monitor the Microservices:
Ways of Working
Set up process for standard product release documentation | Create a Documentation Plan:
Draft the Documents:
Review and Approve the Documents:
Review and Approve the Documents:
Update the Documents: