## Moduls for Automation
Must Needed Functionalities
Data Ingestion
Feature Engineering
Modeling
Model deploy
Logging
Monitoring/Evaluation
Retraining
Notification channel
model registery

## Effort estimation
Modules for Automation | Phase Activity | Effort Estimation (mandays) | Effort Estimation (Weeks) | Effort (wks) with 3 ML Eng
Code Refactoring
Data Ingestion
| Data Read and Ingestion | 8.75 | 1.75 | 0.58333 | Week 4
Feature Engineering
| Data Pre-Processing | 7 | 1.4 | 0.46667 | Week 5
| Data Split | 3.25 | 0.65 | 0.21667 | Week 5
Modeling
| Hyperparamter Tuning | 10 | 2 | 0.66667 | Week 6
| Model Training | 4 | 0.8 | 0.26667 | Week 6
Model deploy
| Model deployment endpoint | 11 | 2.2 | 0.73333 | Week 7
| Model deployment(Batch) | 4.75 | 0.95 | 0.31667 | Week 7
| Model serving endpoint creation | 4.75 | 0.95 | 0.31667 | Week 7
Monitoring/Evaluation
| Model Monitoring and Alerting(Custom) | 15.25 | 3.05 | 1.0167 | Week 8
| data drift and alerting(Custom) | 6.5 | 1.3 | 0.43333 | Week 8
model registery
| Model registry create | 5.25 | 1.05 | 0.35 | Week 9
5.3667
5.25
Model Training |  | 2.5333 |  |  |  | 5.5
|  | 3.0667 |  |  |  | 4.75
Model Deployment | [5 empty] | 4.75
Orchestration
Model Serving
Monitoring
Re-Training
Documentation & KT

## Sheet1
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
code refactoring
CI /CD
ML OPS